## Work Plan
New |  | Start Week | 2023-10-02
Week (Project) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 17 | 18 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Week (Year) | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Starting | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26 | 2024-03-04 | 2024-03-11 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-29 | 2024-05-06
| 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25 | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26 | 2024-03-04 | 2024-03-11 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-29 | 2024-05-06
Weather Data Parser | 2023-10-16: Mile
Interactive mapping tool (location-based static and dynamic data) | 2023-11-06: Mile
Interactive risk mapping tool (adding risk exposure factors) | 2023-12-18: Mile
[1] Bulding the digital mapping tool
1.1. Build a weather data parser from MET Office on a 50 meter grid | bar: 2023-10-02 to 2023-10-16
1.2. Collect statice data layers (elevation, geology, soil and land cover) | bar: 2023-10-16 to 2023-10-23
1.3. Overlay static data layers on the dynamic weather data outcomes | bar: 2023-10-16 to 2023-10-30
1.4. Add a flexible weighing functionality | bar: 2023-10-30 to 2023-11-06
1.5. Dissimination Workshop with the advisory team | bar: 2023-11-13 to 2023-11-20
[2] Adding risk exposure factors
2.1. Collect temporal visitation patterns data from Strava and OS | bar: 2023-11-27 to 2023-12-04
2.2. Add temporal visitation patterns to the mapping tool | bar: 2023-12-04 to 2023-12-11
2.3. Add Wildfire Incident log data and perform priliminary analysis | bar: 2023-12-04 to 2023-12-18
2.4. Dissimination Workshop with the advisory team and risk modellers | bar: 2024-01-08 to 2024-01-15
[3] Refinement and Analysis
3.1.
3.2.
3.3.
[7 empty] | Y | Preparation
[7 empty] | X | Activity